Team Members

- HEID – Beth Landis, Robin Langdon, Chris Davis, Carrie Wheeler, Sara Terry, Rob Pinder, Ben Gibson, Scott Voorhees, Matt Woody, Kimber Scavo, Darryl Weatherhead, Kelly Rimer

- AQPD – Rich Damberg, Mia South

- AQAD – Carey Jang, Jim Kelly, Joe Mangino, Jeanette Reyes, Tyler Fox

- OID – Amanda Kaufman, James Payne

- SPPD – Lisa Conner

Louisville Multi-Pollutant Project

Update

  - November 30th Meeting

    - Redesignations update

    - Sharing BenMAP data with Center for Health Equity (Angela Graham)

    - Air Quality Action Partners End of Year Report status

    - MP Strategy Document status

    - Next Steps:

      - Airport / UPS Conversations

      - Development of Milestones / MP Strategy Document

Next Steps

  - Schedule Jan/Feb meeting with LMAPCD

NEXUS

  - NEXUS 2.0 available - https://gaftp.epa.gov/Air/aqmg/cjang/NEXUS/NEXUS%202.0/

  - Development team creating beta version

  - Recent Upgrades & Improvements - NEXUS “1.5” (Jan 2021)  NEXUS “2.0” (Sept 2021)

  - Upgraded Metrics (PM2.5, O3, Air Toxics + EJ/Demographics as 4th metric)

  - New/updated data inputs and functions:

    - EJ/Demographic data (from EJSCREEN), Tribal areas, Advance areas, Attainment/DVs data, etc.

    - Updated 2017 emissions data (including GHG & Sector mapping)

    - “Source Category Emissions” module and “Sector Emissions Summary” module

    - Preliminary 2017 BenMAP risk data & draft “Monitoring sites/data” module

  - Completed EPA region “Table Generator”

  - Upgraded “Data Query” module & “Data Input” module

  - O3 and PM2.5 risk data (BenMAP) delivered

  - Developed “Monitoring sites/data module” prototype

- NEXUS “2.2” (Dec. 2021) (Demo version today: 12/14/2021)

  - Download at: https://gaftp.epa.gov/Air/aqmg/cjang/NEXUS/MP_Team/NEXUS_2.2/ with quick tutorial PPT)

  - Updated 2017 BenMAP risk and fused data for PM & O3

  - Upgraded “Monitoring sites/data” module

  - “Proximity analysis module” prototype for MP risks and EJ

- NEXUS “2.3” (Feb. 2022) (upcoming)

  - 2017 updated air toxics risk data (expected to receive: Dec. 2021)

- Recent Briefings

  - 11/2/2021 – Regional APMs

  - 11/8/2021 – Regional APMs Demo

  - 11/16/21 - R1 (RARE Project)

  - 11/28/21 - AQAD All-Hands

  - 11/23/21 - R3 NEXUS Beta Testers

- Beta Testers

  - R1- Susan Lancey, Shutsu Wong & Emily Bolger

  - R2 – Ysabel Barron

  - R3 – Cynthia Stahl, Carol Ann Gross-Davis & Jessie Fry

  - R4/LMAPCD – Rick Gillam & Byron Gary

  - R5 – Alexis Cain & Margaret Sieffert

  - R6 – Nia Riddick

Next Steps

  - NEXUS updates

    - Complete update to 2017 fused air toxics and risk data (not received yet, planned for Dec.) from current 2014 data

  - MP Team Members

    - Download NEXUS 2.0 and/or 2.2 and provide feedback

  - Winter 2021

    - Develop a beta NEXUS version for testing (and prepare for public release?)

    - Briefings/demos for:

        - SPPD READY Team?

        - TBD - MJOs

    - Finalize online User’s Manual

    - Develop packets for regions

  - Consider incorporating Mexico (border) information into NEXUS

Possible Future MP Work

  - FL and/or TN – raised by R4 as possibilities

  - Detroit, MI – raised by R5/MEGLE as possibly interested in MP work in conjunction with Michigan-Ontario Ozone Source Experiment (MOOSE) – was rescheduled to summer 2021 due to Covid-19

  - Portland, OR – raised by R10 as potential partner worth exploring during Advance Workgroup Call – sent materials to Karl Pepple to determine interest

  - US/Mexico Border - cross-border MP pilot program possible after success is demonstrated with smaller projects (EI development, improved monitoring, trainings) – interest from Guy Donaldson (El Paso) & Idalia Perez (Imperial & San Diego)

  - Connecticut – R1 RARE Project with CT DEEP and ORD “Improving State-Level Multi-Pollutant Planning in Connecticut with GLIMPSE”.

    - Support CT's ozone attainment planning efforts through wholistic, systems analysis of state clean energy and climate policies and their multi-pollutant, environmental impacts​

    - Enhance GLIMPSE modeling tool development so that GLIMPSE can more effectively meet state and regional analytical needs for air quality planning​

    - Demonstrate the benefits of integrating clean energy strategies (EE & RE) into criteria pollutant planning

Demos

  - SaRA Tool – Matt W.

  - NEXUS 2.2 (Proximity Analysis) – Carey J.

Next Team Meeting Scheduled for Wednesday, January 19th at 3pm

Happy Holidays!