Team Members

- HEID – Beth Landis, Robin Langdon, Chris Davis, Carrie Wheeler, Sara Terry, Rob Pinder, Ben Gibson, Amy Vasu, Kimber Scavo, Darryl Weatherhead

- AQPD – Rich Damberg

- AQAD – Carey Jang, Joe Mangino, Tyler Fox

- OID – Amanda Kaufman

NEXUS

Update

  - Developed the NEXUS prototype (alpha version) to provide visualization and analysis functions of multi-pollutant air quality issues (PM2.5, O3 and air toxics) on a national level

  - Developed the NEXUS beta-version with new design of the three key modules (Data Viewer, Data Query, and Data Input) and regional analysis (Phase 2), based on team’s feedback

  - Continued testing, debugging and improving NEXUS Tool based on feedback received

  - Drafted online User’s Manual

  - Several briefings/demos

    - July - MP Team demo

    - September – AQAD (+HEID) Technical Meeting Briefing

    - November – MP Team Demo & Air Toxics Group Demo

    - December – AQPD Briefing

Next Steps

  - Winter 2020/2021 –

    - MP Team Members - download NEXUS 1.5 via EISD and provide feedback

    - Incorporate feedback received (air toxics group)

    - Briefings/demos for:

        - OID

        - SPPD

        - Peter

        - Region 4/Louisville

        - APMs

        - MJOs

    - Finalize online User’s Manual

Louisville Multi-Pollutant Project

Update

  - November Meeting with LMAPC

    - Shared initial BenMAP run results using county level health data

    - Discussed different ways to pool the data – East/West, percent minority, urban/suburban, etc.

  - December call with LMAPCD

    - Discussed regulated sources and need for coordination with regulatory partners at KYDAQ, IDEM & R5

Next Steps

  - BenMAP

    - Explore best ways to pool data, schedule follow-up meeting if necessary

  - December 16th call with R4 & R5

    - Bring R5 up to speed on the project and discuss how best to coordinate going forward

  - Schedule call in January to discuss next steps with LMAPCD’s regulated sources and regulatory partners at KYDAQ, IDEM & R5

General Multi-Pollutant

Update

  - Possible Future MP Work:

    - FL and/or TN – raised by R4 as possibilities – R4 currently exploring interest

    - Detroit, MI – raised by R5/MEGLE as possibly interested in MP work in conjunction with Michigan-Ontario Ozone Source Experiment (MOOSE) – trying to reschedule to summer 2021 due to Covid-19

    - Portland, OR – raised by R10 as potential partner worth exploring during Advance Workgroup Call – sent materials to Karl Pepple to determine interest

    - US/Mexico Border - cross-border MP pilot program possible after success is demonstrated with smaller projects (EI development, improved monitoring, trainings)

  - November 2020 – email sent to APMs with a heads up about collective efforts in the MP and Advance programs that will be coming

Next Steps

  - Winter 2020/2021

    - Continue gauging interest in MP partnerships in FL, TN, Detroit, Portland and/or US/Mexico Border

    - Discuss MP/Advance email on future APM call

    - Develop regional packets using NEXUS Tool

Mobile Control Measures Project

Update

  - Spring 2020 - Requested courtesy review of results by OTAQ

  - Summer 2020 –

    - Call with OTAQ to provide background on the purpose of the project, what it is intended to be used for, who the audience would be, etc.

    - OTAQ provided feedback

    - Began reviewing comments from OTAQ to determine best way to incorporate

Next Steps

  - Winter 2020/2021 –

    - Finish incorporating comments from OTAQ

    - More broadly share workbook

Next Team Meeting Scheduled for Tuesday, January 12th at 11am