Team Members

- HEID – Beth Landis, Robin Langdon, Chris Davis, Carrie Wheeler, Sara Terry, Rob Pinder, Ben Gibson, Amy Vasu, Kimber Scavo, Darryl Weatherhead

- AQPD – Rich Damberg

- AQAD – Carey Jang, Joe Mangino, Tyler Fox

- OID – Amanda Kaufman

Louisville Multi-Pollutant Project

Update

  - Spring 2020 - Louisville Metro Health Department (LMHD) provided higher spatial resolution data for BenMAP that has required a significant amount of QA

  - Summer 2020 – Chris & Ali QA’d the data provided from LMHD

    - Meeting this morning (8/25) to discuss significant data gaps and how to proceed

  - August 2020 – call with LMAPCD to discuss Multi-Pollutant Stakeholder Group Final Report and next steps

Next Steps

  - September 2020 –

    - Coordinate with LMAPCD and LMHD to deal with data gaps in order to complete BenMAP analysis and discuss how to best communicate results

    - Call with LMAPCD regarding control strategies and AQMP

General Multi-Pollutant

Update

  - Possible Future MP Work:

    - FL and/or TN – raised by R4 as possibilities – R4 currently exploring interest

    - Detroit, MI – raised by R5/MEGLE as possibly interested in MP work in conjunction with Michigan-Ontario Ozone Source Experiment (MOOSE) – trying to reschedule to summer 2021 due to Covid-19

    - Portland, OR – raised by R10 as potential partner worth exploring during Advance Workgroup Call – sent materials to Karl Pepple to determine interest

    - US/Mexico Border - cross-border multi-pollutant pilot program possible after success is demonstrated with smaller projects (e.g. EI development, improved monitoring, trainings)

  - August 2020 - Drafted email that gives Regional contacts a heads up about collective efforts in the MP and Advance programs that will be coming this fall

Next Steps

  - Fall/Winter 2020

    - Continue gauging interest in MP partnerships in FL, TN, Detroit, Portland and/or US/Mexico Border

    - Send MP/Advance email to regions so they are aware of next steps and can prepare to engage

    - Develop regional packets using NEXUS Tool

NEXUS

Update

  - Spring 2020 - developed the NEXUS prototype (alpha version) to provide visualization and analysis functions of multi-pollutant air quality issues (PM2.5, O3 and air toxics) on a national level

  - Summer 2020 –

    - Developed the NEXUS beta-version with new design of the three key modules (Data Viewer, Data Query, and Data Input) and regional analysis (Phase 2), based on team’s feedback

    - Demoed NEXUS at the July MP Team Meeting

    - Continued testing, debugging and improving NEXUS Tool based on feedback received

    - Drafted online User’s Manual

Next Steps

  - September 2020 - MP team members download NEXUS and provide feedback ASAP

  - Fall 2020 –

    - Begin briefings/demos for:

      - Chet/Erika => Peter

      - Region 4/Louisville

      - APMs

      - MJOs

    - Finalize online User’s Manual

Mobile Control Measures Project

Update

  - Spring 2020 - Requested courtesy review of results by OTAQ

  - Summer 2020 –

    - Call with OTAQ to provide background on the purpose of the project, what it is intended to be used for, who the audience would be, etc.

    - OTAQ provided feedback

    - Began reviewing comments from OTAQ to determine best way to incorporate

Next Steps

  - Fall 2020 –

    - Finish incorporating comments from OTAQ

    - More broadly share workbook

Next Team Meeting Scheduled for Tuesday, September 22nd at 11am