Team Members

- HEID – Beth Landis, Robin Langdon, Chris Davis, Carrie Wheeler, Sara Terry, Rob Pinder, Ben Gibson, Amy Vasu, Kimber Scavo, Darryl Weatherhead

- AQPD – Rich Damberg

- AQAD – Carey Jang, Joe Mangino, Tyler Fox

- OID – Amanda Kaufman

Louisville Multi-Pollutant Project

Update

  - BenMAP

    - Higher spatial resolution data provided from LMHD has been QA’d

    - Initial BenMAP run using county level health data is promising and a significant improvement over what was already in BenMAP

  - October Meeting with LMAPCD

    - LG&E upheld their commitment to maintaining total NOx emissions from Mill Creek’s four units ≤ 15 tons per day during the 2020 ozone season (April 1- October 31)

        - On O3 exceedance days from 2016-2019, NOx emissions from these units ranged from just over 15 to as high as 36 tons per day

    - Saw a 30% reduction in VMT during the peak of COVID – it has largely rebounded but peak hours are still off

    - Despite the LG&E agreement & VMT reductions, preliminary numbers show one site (Cannon’s Lane) with a 4th highest truncated value over the standard

        - Preparing to move from marginal to moderate nonattainment for O3

        - If summer 2021 is really good, they could request early certification for clean data because they will be dropping a high value (77 ppb for 2018)

        - Cannon’s lane is the only site remaining above the standard

    - Meteorology is key, and it is becoming more apparent that coordination with IN and the state of KY are necessary to reach necessary O3 reductions in Jefferson County

    - Updates from MPSG leads

Next Steps

  - BenMAP

    - Divide health data into east/west bins

  - November Call with LMAPCD

    - Share & discuss BenMAP results and determine next steps for communicating results

    - Next steps for implementing recommendations from MPSG

    - Next steps for determining control strategies

    - Discuss AQMP plans

General Multi-Pollutant

Update

  - Possible Future MP Work:

    - FL and/or TN – raised by R4 as possibilities – R4 currently exploring interest

    - Detroit, MI – raised by R5/MEGLE as possibly interested in MP work in conjunction with Michigan-Ontario Ozone Source Experiment (MOOSE) – trying to reschedule to summer 2021 due to Covid-19

    - Portland, OR – raised by R10 as potential partner worth exploring during Advance Workgroup Call – sent materials to Karl Pepple to determine interest

    - US/Mexico Border - cross-border multi-pollutant pilot program possible after success is demonstrated with smaller projects (e.g. EI development, improved monitoring, trainings)

  - August 2020 - Drafted email that gives Regional contacts a heads up about collective efforts in the MP and Advance programs that will be coming this fall

Next Steps

  - Fall/Winter 2020

    - Continue gauging interest in MP partnerships in FL, TN, Detroit, Portland and/or US/Mexico Border

    - Send MP/Advance email to regions so they are aware of next steps and can prepare to engage

    - Develop regional packets using NEXUS Tool

NEXUS

Update

  - Developed the NEXUS prototype (alpha version) to provide visualization and analysis functions of multi-pollutant air quality issues (PM2.5, O3 and air toxics) on a national level

  - Developed the NEXUS beta-version with new design of the three key modules (Data Viewer, Data Query, and Data Input) and regional analysis (Phase 2), based on team’s feedback

  - Demoed NEXUS at the July MP Team Meeting

  - Continued testing, debugging and improving NEXUS Tool based on feedback received

  - Drafted online User’s Manual

  - Briefed Chet & Erika in September AQAD Technical Meeting

  - Success downloading NEXUS 1.5 through request to EISD

Next Steps

  - Fall/Winter 2020 –

    - MP Team Members - download NEXUS 1.5 via EISD and provide feedback

    - Begin briefings/demos for:

        - Peter

        - Region 4/Louisville

        - APMs

        - MJOs

    - Finalize online User’s Manual

Mobile Control Measures Project

Update

  - Spring 2020 - Requested courtesy review of results by OTAQ

  - Summer 2020 –

    - Call with OTAQ to provide background on the purpose of the project, what it is intended to be used for, who the audience would be, etc.

    - OTAQ provided feedback

    - Began reviewing comments from OTAQ to determine best way to incorporate

Next Steps

  - Fall 2020 –

    - Finish incorporating comments from OTAQ

    - More broadly share workbook

Next Team Meeting Scheduled for Tuesday, November 17th at 11am