NEXUS Tool: Project and Coordination Plan for FY21

Feb. 23, 2021

Short-term Goal:  Provide for near-term updates to current tool aimed at updating existing data to 2017, adding new data reflecting 2017, and revise or add to current set of metrics/indicators.

Resources:  In-house staff time with expected OAQPS/AQAD funding of $50k to support this short-term project

Update existing data to 2017: (What data, where from, who responsible)

- O3 and PM2.5 emissions and source data

- Data: “2017 NEI_County_CAPs.gdb” and “2017 NEI_Facility_HAPs_ CAPs.gdb”

- Coordination: w/ EIAG (Allison E. & Sharon P.)

- O3 and PM2.5 concentrations data

- Data: “2017 fused O3 and PM2.5 air quality surface data” (generated for CDC project)

- Coordination: w/ AQMG (Sharon P.)

- O3 and PM2.5 risk data (consistent with concentration data)

- Data: “2017 O3_PM2.5 Fused Ambient_Risk.gdb” in census tract-level (BenMAP output)

- Coordination: w/ MP Team (Beth L. & Chris D. & Elizabeth C.)

- Air toxics emissions and source data

- Data: 2017 “NEI HAPs Emissions”” and “Sector-based” HAPs emissions

- Coordination: w/ EIAG (Allison E. & Sharon P.) & ATAG (Matt W.)

- Air toxics concentration data

- Data: 2017 air toxics modeled results (i.e., hybrid CMAQ/AERMOD output)

- Coordination: w/ AQMG (Sharon P. & James T.)

- Air toxics risk data (consistent with modeled data)

- Data: “2017 NATA Risk.gdb” in census-tract level

- Coordination: w/ Air Toxics Team (Matt W. & Amy V.) & MP Team (Beth L.)

- Geographic boundaries:  confirm Advance areas and NAAs, add Tribal boundaries

- Data: Updated Advance areas, updated NAAs, Tribal areas

- Coordination: w/ MP team (Beth L., Rich D., Doug S., Amanda K. & James Payne)

Additional 2017 data: (What data, where from, who responsible)

- Socio-economic and Demographic data (primarily for EJ purposes)

- Data: Various data at census tract-level with many available from EJSCREEN database

- Coordination: w/ AQMG (Jim K.) & MP team & OID (Matt W., Beth L., Amanda K., Sara T. & EJ team)

- O3 and PM2.5 monitoring data

- Data: AQS - O3 and PM2.5 data

- Coordination: w/ AQAG (Joe M. & Brett G. & Ben W.)

- Air toxics monitoring data

- Data: Air toxics data – Heavy metal HAPs & Gas/VOC HAPs

- Coordination: w/ AQAG (Joe M. & Jeanette Reyes) & AAMG (Doris Chen) & Air Toxics team (Matt W. & Amy V.)

- Greenhouse Gas Emissions:

- Data: GHG source/sector/geographic emissions and black carbon data

- Coordination: w/ EIAG (Rich M., Ron Ryan) & MP team (Rob P.)

Updates to metrics/indicators:

- O3 and PM2.5 risk estimates:  how calculated, appropriate/consistent terminology, spatial resolution

- Mortality risk focus, other metrics to consider

- Schedule discussion amongst team as part of generating 2017 estimates

- Coordination: w/ MP team (Neal F. & Elizabeth C., Chris D.) & AQMG (Jim K. & Heather S.)

- Air toxics risk estimates:  how calculated, appropriate/consistent terminology, spatial resolution (list of suggestions provided by Matt W./ATAG)

- National screening level: County-level (average & max); cancer / non-cancer (by pollutant/combinations); incidence-based? other?

- Area specific level:  Census and/or block-level; cancer, non-cancer (by pollutant/combinations);

- Coordination: w/ Air Toxics team (Matt W. & Amy V.)

- Multi-pollutant considerations of risk and ranking areas

- Use of weighted indicators to allow for relative rankings and area comparisons

- Discussion across team on how, if appropriate, to combine risk estimates and effectively rank areas

- Coordination: w/ MP team (Beth L.) and Air Toxics team (Matt W. & Amy V.)

- EJ metrics/indicators

- What data to define race, income, tribal entities; how currently use these data for EJ?

- What metrics/indicators of inequities?   Currently used or to be developed?

- Coordination: w/ AQMG (Jim K.) and MP team (Beth L. & Matt W.) & OID (Amanda K., Sara T. & EJ team)

Other Updates/improvements:

- Update online NEXUS User’s Manual

- Upgrade “Data Query” module’s configuration window and map display

- Consolidate “Table Generator” function reports for O3, PM2.5, and Air Toxics

- Highlight common facilities under “Major emission sources” table

- Include “sector-based” & total emissions for selected region under “Major emission sources” table

- Provide option to select “top risk percentile” based on ranking of nation or selected region only

==========================================================================

Long-term Goal:

(1) Develop a NEXUS beta-testing version for use by EPA Regions and considerations of public release

(2) Develop a high-resolution air toxics module with area and/or source focus at census tract- and/or block-level and with EJ analytics for proximity analysis of air toxics based on demographic data

(3) Explore multi-pollutant proximity analysis with risk data to inform EJ screening

Resources:  Potential funding support from MP team and/or Air Toxics team?

Development efforts:

(1) NEXUS Beta-testing version

- Based on updated 2017 NEXUS and NATA database

- Upgrade online User’s Manual

- Create beta-testing group consisting of internal and external users

- Coordination: w/ MP Team (Beth L.)

(2) High-resolution Air Toxics module

- Develop a new air toxics module with proximity analysis capabilities and identification of risk drivers

- Develop area/source layer at census tract- or block-level air toxics

- Coordination: w/ Air Toxics team (Matt W. & Amy V.), MP team and AQMG

(3) Explore multi-pollutant proximity analysis with risk data to inform EJ screening

- Develop multi-pollutant proximity analysis functions linking to EJ indicators

- Develop area/source layer at census tract-level for PM2.5 and ozone

- Coordination: w/ AQMG (Jim K.), MP team and OID

=================================

2/22/2021 meeting: Tyler, Marc, Allison, Rich, Sharon, James, Carey

- Quick overview of current 2014 NEXUS dataset & format (4:00-4:10 pm)

- 2017 emissions data (facility & sector) for CAPs & HAPs & GHG (4:10-4:35 pm)

  - Update need:

    - CAPs emissions updated to 2017 for Facility emissions and major sectors (pt/nonpt/road/nonroad/event)

    - HAPs emissions updated to 2017 for Facility emissions

  - New data need:

    - GHG emissions (county or census tract level) for Facility emissions and major sectors

    - HAPs emissions for facility's industrial sector groups (coke ovens, refineries, etc.) and major sectors

- 2017 fused AQ data for air toxics, PM & O3 to be provided for risk estimate (4:35-5:00 pm)

  - Update need: (from CAPs/HAPs modeling platform)

    - O3 & PM fused conc. (model & monitor) updated to 2017

    - Air toxics fused conc. (hybrid CMAQ & AEROMOD) updated to 2017

  - New data need:

    - Facility-specific air toxic data (for each facility) for risk estimate

    - New species need (PFAS:no, Diesel PM & Mn; Hg & Pb:non cancer)

=================================

NEXUS Tool: Project and Coordination Plan for FY21

- O3 and PM2.5 emissions and source data

- Data: “2017 NEI_County_CAPs.gdb” and “2017 NEI_Facility_HAPs_ CAPs.gdb”

- Coordination: w/ EIAG (Allison E. & Sharon P.)

- O3 and PM2.5 concentrations data

- Data: “2017 fused O3 and PM2.5 air quality surface data” (generated for CDC project)

- Coordination: w/ AQMG (Sharon P.)

-  Air toxics emissions and source data

- Data: 2017 “NEI HAPs Emissions”” and “Sector-based” HAPs emissions

- Coordination: w/ EIAG (Allison E. & Sharon P.)

- Air toxics concentration data

- Data: 2017 air toxics modeled results (i.e., hybrid CMAQ/AERMOD output)

- Coordination: w/ AQMG (Sharon P. & James T.)

- Greenhouse Gas Emissions:

- Data: GHG source/sector/geographic emissions and black carbon data

- Coordination: w/ EIAG (Rich M., Ron Ryan)

=================================