## Main
Person | 2008v2 Sector or Dataset | ISSUE(s) | Description | QA | Selection for 2008v2 (GPR) | Modeling File Date | status | Documentation | EIS Data summaries | Notes for 2011
Laurel | Onroad | how do we handle the lack of road type and other (if they exist) SCC disparities? Make sure no road type summaries are done? Do these need to be documented? | MOVES2008 for non -Calif Calif submitted for Calif; overwrites for emissions from polls not present in MOVES for SCC/modes | make sure no unspeciated chromium | AFTER POINT -- may not be released with rest of 2008v2 if doesn't get done right | not needed (Modeling team will create modeling inputs via SMOKE/MOVES) | 12/23-12/26 is estimated date MOVES to go into EIS |  |  | tell them how to provide speciated chromium and only accept that?
Laurel | Nonroad | Decide which SLT data to use vs which EPA data to use. Do a selection for what is chosen. | NMIM with or without state inputs (EPA) Calif submitted for Calif Any other agency submitted ? Tribal? | make sure no unspeciated chromium | 2011-12-29 | not needed (Modeling team already has monthly from CDC project, and NEI will not be consistent due to Calif)
Madeleine | Point | South Dakota/PR/VI missing. How to sum up Hg emissions and will we be able to release them? | State data with EPA datasets for Airports, Rail, chromium speciation, coke ovens, gold mines, EGU, EPA RULE EGU, EPA_OTHER, Overwrites,PM Aug , TRI, HAPAUG, NATA | (1) make sure no unspeciated chromium in individ datasets and selection ; (2) QA individ datasets (see POINT) and (3) after selection is done, compare RAS to v2 at facility level to see where v2 >>RAS and make sure that is ok. | 2012-01-10 | 2012-01-13 |  |  |  | bring back coke oven emissions and retire BSO&MCSO
Roy | Nonpoint | Get WA Ag state submittal into state data. Address EMT issues. |  | Make sure EPA vs state reported Ag fire is not double counted. make sure no unspeciated chromium | 2012-01-03 | 2012-01-06
Tesh | Prescribed/Wild/Unclassified (mix of Event and Prescribed removed from nonpoint) | Will be double counting btween tribal prescribed (submitted in nonpoint). Where we use state data, we use no EPA data even if SCC/counties in EPA data are different; for these states, the emissions are significantly smaller than what SMARTFIRE estimated. | county-level prescribed, wild and unclassified fires; some of which were estimated by SMARTFIRE, others provided by states in either EVENT or nonpoint. |  | no selection - Josh to create county-SCC summary data for posting outside of EIS based on instruction from Tesh DATE for Summaries NEEDED | not needed | need Washington State to submit Ag to nonpoint. Need to develop instructions for Josh. Need to compute HAPs from state-level HAP-to-PM2.5 ratios (from EPA data) where we will chose state-submitted data. |  |  | get rid of EVENTS? If not really need an SCC cleanup (remove AG events and managed burning EVENT SCCs, remove "open fire" nonpoint SCC)

## ONROAD
Person | Dataset | Description | Hierarchy | QA | Status
Laurel | MOVES | MOVES for entire country other than Calif (AK, HI, VI, PR?) | 1 |  | load into EIS 12/23-12/26
Laurel | EPA Correction Dataset - Onroad | zero out emissions from pollutant/mode/process combinations that are not present in MOVES | don't use
Laurel | Calif | Calif submission -- no road types | don't use
Override Type | Override Value | Overwrite Hierarchy
State | California | 1, EPA Correction Dataset - Nonroad 2. Responsible Agency Data Set
Pollutant | 1746016 | 2,3,7,8-Tetrachlorodibenzo-p-Dioxin
Pollutant | 19408743 | 1,2,3,7,8,9-Hexachlorodibenzo-p-Dioxin
Pollutant | 3268879 | Octachlorodibenzo-p-Dioxin
Pollutant | 35822469 | 1,2,3,4,6,7,8-Heptachlorodibenzo-p-Dioxin
Pollutant | 39001020 | Octachlorodibenzofuran
Pollutant | 39227286 | 1,2,3,4,7,8-Hexachlorodibenzo-p-Dioxin
Pollutant | 40321764 | 1,2,3,7,8-Pentachlorodibenzo-p-Dioxin
Pollutant | 51207319 | 2,3,7,8-Tetrachlorodibenzofuran
Pollutant | 55673897 | 1,2,3,4,7,8,9-Heptachlorodibenzofuran
Pollutant | 57117314 | 2,3,4,7,8-Pentachlorodibenzofuran
Pollutant | 57117416 | 1,2,3,7,8-Pentachlorodibenzofuran
Pollutant | 57117449 | 1,2,3,6,7,8-Hexachlorodibenzofuran
Pollutant | 57653857 | 1,2,3,6,7,8-Hexachlorodibenzo-p-Dioxin
Pollutant | 600 | Dioxins/Furans as 2,3,7,8-TCDD TEQs - TEQ scheme unspecified
Pollutant | 60851345 | 2,3,4,6,7,8-Hexachlorodibenzofuran
Pollutant | 626 | Dioxins/Furans as 2,3,7,8-TCDD TEQs -I/89
Pollutant | 627 | Dioxins/Furans as 2,3,7,8-TCDD TEQs - WHO/98
Pollutant | 67562394 | 1,2,3,4,6,7,8-Heptachlorodibenzofuran
Pollutant | 70648269 | 1,2,3,4,7,8-Hexachlorodibenzofuran
Pollutant | 72918219 | 1,2,3,7,8,9-Hexachlorodibenzofuran

## POINT
Person | Dataset | description | hier-archy | hierarchy rationale | QA | status
Ron | EPA EGU rule (name not yet in EIS) | Speciated chromium, managnese, Pb, arsenic, Se, Hg, for units subject to MATS and 0 outs for processes in WV and ______? to ensure no double counting | 1 | Some of the MATS emissions uses unit-specific Efs based testing, and the non-tested units use updated Efs generated for the MATS rule. Would like consistency between key metal HAP and Hg emissions summarized in MATS rule and NEI (NEI will be released shortly after MATS). | RON? please add or refer to document/location | RTI to deliver 12/15
Madeleine | EPA Overwrite 1.5 | contains emissions for airportAcenaphthylene only-- all other outliers previously in this dataset for 2008v1.5 were resolved and removed from this dataset. | 2 | Must go ahead of SLT data because will need to zero out SLT acenaphythene. | make sure only Acenaphthylene and the work-around dioxin to be dropped is present in this dataset. DONE. Note only 1 SCC in dataset: 2275050012 | doing report for QA. Also need SCC code for acenaphytene for documentation
Roy | EPA PM Augmentation, v2 | contains complete and consistent set of PM species where SLT data missing or have inconsistent PM species Uses PM calculator for covered SCCs. For others, checks/corrects discrepancies or missing PM species using basic relationships such that PM2.5< or equal PM10. | 3 | Must go ahead of SLT data because will need to correct inconsistent SLT data (for example, replaces Iowa PM con because it is larger than PM PRI because Iowa reported total PM under PM-CON). | Roy please add or refer to document/location | needs to be loaded int EIS
Madeleine | EPA Chromium Split v2 | contains zeroed out total chromium (7440473) and hex and trivalent chromium based on reconciliation and speciation of chromium using reg codes and SCC codes. | 4 | Must go ahead of SLT data because will need to zero out SLT total chromium so as not to double count it. | Make sure sum of hex and tri = RAS chromium. Make sure all unspeciated chromium has zero emissions. Make sure that wherevere there is hex and whereever there is tri, there should be an unspeciated value that Is zero.
Madeleine | EPA_OTHER | HAP emissions for which SLT did not wish to or were unable( in the timeframe provided) incorporate into their datasets. Includes emissions based on updated data from the EAF test program or MWC compliance data and Region 2 benzene and coke oven emissions for Tonawanda coke based on recent testing, as well as revised state provided emissions developed during the 2008v2 NEI "NATA review" which focused on Hg and high risk facilitie sfrom the 2005NATA. | 5 | Must go ahead of SLT data because in many instances, is a more updated value. In some cases there is no SLT data and this dataset will gapfill. | Make sure no unspeciated chromium | need to load high risk and Hg_other
Madeleine | SLT submitted data |  | 6 | SLT data. It needs to be selected after: (1) PM aug due to need for overwriting PM CON or any other bad state data, (2) chrom speciation because the apporach involves not only speciating but also adjusting hex or tri due to inconsistencies), (3) EGU rule data because it uses upated source test data, (4)EPA_OTHER data because states did not want to replace their values in their dataset and we did want to choose Region 2's data above NY for Tonawanda and (5) EPA overwrite data -- which will correct a bad acenaphylene value from certain aircraft |  |  | 6 | for nebraska and connecticut EGU is before SLT
Laurel | EPAAirports1109 | emissions for aircraft sccs (including engine types) computed by EPA for approximately 18,000 airports from ______ database. | 7 | should go below state data since state data are preferred. Does not overlap with any other point dataset | Need from Laurel or considered done since this file hasn't changed since v1 |  | 13
Laurel | EPA Rail |  | 8 | should go below state data since state data are preferred. Does not overlap with any other point dataset | Need from Laurel or considered done since this file hasn't changed since v1 |  | 14
Ron | EPA EGU v1.5 | CAMD NOX, SO2 and EPA-estimated other HAPs from CAMD heat input and Efs (same Efs as in 2002 NEI other than PM for natural gas and IGCC which were updated with more recent data). | 9 | Other than the 2 overrides, we prefer to use state data which may reflect unit-specific testing or Efs that were tie to actual control efficienies rather than default values. | RON? please add or refer to document/location
Madeleine | 2008 EPA Rule Data from OAQPS/SPPD | Hg only from the following categories (thus far): MWC (compliance data, per SPPD this is based on compliance tests), EAF (test data from 2010, EFs develoed were -- applied to 2009 throughputor capacity), and Hg chloralkali (SPPD computed using TRI and other information). | 10 | This goes below state data. If a state preferred to use the rule data, we would put it in EPA_Other in addition to this dataset. Main purpose is to gapfill where there is no SLT reported. | See document: QA POINT details (C:\Documents and Settings\mstrum\My Documents\POINT\2008v2) | in EIS and QA'd
Sally? | Nevada gold mines | Hg emissions data from Nevada Mercury Control Program (NMCP) - Annual Emissions Reporting http://ndep.nv.gov/bapc/hg/aer.html other than Homestake Mining Co. – Ruby Hill and Barrick Goldstrike Mines, Inc based on validated 2009 test data provided by Adele Malone (11/7/2011) via an internal document (CY2008 NMCP Hg ESTIMATION.XLS) | 11 | Does not overlap with other data sets (we pulled gold mines for Nevada out of TRI) so it doesn't matter what order. | Sally? | in EIS
Madeleine | EPA coke oven | coke oven emissions (BSO - 141 and MCSO - 142) computed from AP-42 provided by a few states that did not report coke oven emissions and that did not want to add it into their inventories. For Tonawanda coke, data were a combination of NATA2005 and more updated test data provided by Region 2. | 12 | Purpose of this dataset is to gapfill missing coke oven emissions -- it can go in any order since it does not conflict with any other dataset. Choose it to go below state data | Looked at facility totals to make sure no outliers (nothing huge when compared to NATA2005 coke oven). See: C:\Documents and Settings\mstrum\My Documents\POINT\2008v2\cokeoven\2005 NATA coke ovenfromsppd__QA EIS COKE OVEN DATASET BY COMPARISON.xlsx | in EIS and QA'd
Madeleine | EPA TRI Augmentation v2 | TRI data manually-assigned facility level emissions data to EIS processes for the NATA review categories of: EAF, goldmines, cement, highrisk, other_hg; default -assigned to processes using surrogate CAPs for approximately _____ TRI facilities that match to EIS facilities | 13 | Purpose of this dataset is to gapfill HAPs | Make sure no unspeciated chromium. | not yet developed
Madeleine | EPA HAP Augmentation v2 | HAP data computed from SLT criteria pollutant data using emission factor ratios (HAP to VOC, HAP to PM10-FIL) based on webfire. Hg-to PM10fil for boilers was extended to be more inclusive of different boiler types by using the same webfire-based ratios for boilers that had the same fuel type (but different SCC) as a webfire boiler but were missing from webfire | 14 |  | Make sure no unspeciated chromium
Madeleine | EPA 2005NATA values pulled forward to gapfill | HAP and Hg emissions resulting from 2008v2 NATA review where 2005 NATA emissions of high risks and Hg from certain categories were presented to states. Agencies recommended or agreed that 2005NATA would be a reasonable gapfill approach because facility was still in operation in 20008 and no other alternatives existed (e.g., no TRI data) for gapfilling. | 15 | Purpose of this dataset is to gapfill HAPs. Does not overlap with any other dataset but because it is pulling data from a previous year to gapfill put it last. | Make sure no unspeciated chromium
Ron | OFFSHORE dataset (name needs to be entered | Emissions from oil ang gas platforms in the gulf of mexico (Federal waters) developed by Bureau of Ocean Energy Management (http://www.gomr.boemre.gov/PI/PDFImages/ESPIS/4/5056.pdf) criteria pollutants only | 16
Override Type | Override Value | Overwrite Hierarchy
State | Connecticut | Move EPA EGU v1.5 to position 6 (before SLT data) so because the SLT data for EGUs were put at the wrong units
County | Douglas, Nebraska | Move EPA EGU v1.5 to position 6 (before SLT data) so because the SLT data for EGUs were put at the wrong units
Pollutant | 1746016 | 2,3,7,8-Tetrachlorodibenzo-p-Dioxin
Pollutant | 19408743 | 1,2,3,7,8,9-Hexachlorodibenzo-p-Dioxin
Pollutant | 3268879 | Octachlorodibenzo-p-Dioxin
Pollutant | 35822469 | 1,2,3,4,6,7,8-Heptachlorodibenzo-p-Dioxin
Pollutant | 39001020 | Octachlorodibenzofuran
Pollutant | 39227286 | 1,2,3,4,7,8-Hexachlorodibenzo-p-Dioxin
Pollutant | 40321764 | 1,2,3,7,8-Pentachlorodibenzo-p-Dioxin
Pollutant | 51207319 | 2,3,7,8-Tetrachlorodibenzofuran
Pollutant | 55673897 | 1,2,3,4,7,8,9-Heptachlorodibenzofuran
Pollutant | 57117314 | 2,3,4,7,8-Pentachlorodibenzofuran
Pollutant | 57117416 | 1,2,3,7,8-Pentachlorodibenzofuran
Pollutant | 57117449 | 1,2,3,6,7,8-Hexachlorodibenzofuran
Pollutant | 57653857 | 1,2,3,6,7,8-Hexachlorodibenzo-p-Dioxin
Pollutant | 600 | Dioxins/Furans as 2,3,7,8-TCDD TEQs - TEQ scheme unspecified
Pollutant | 60851345 | 2,3,4,6,7,8-Hexachlorodibenzofuran
Pollutant | 626 | Dioxins/Furans as 2,3,7,8-TCDD TEQs -I/89
Pollutant | 627 | Dioxins/Furans as 2,3,7,8-TCDD TEQs - WHO/98
Pollutant | 67562394 | 1,2,3,4,6,7,8-Heptachlorodibenzofuran
Pollutant | 70648269 | 1,2,3,4,7,8-Hexachlorodibenzofuran
Pollutant | 72918219 | 1,2,3,7,8,9-Hexachlorodibenzofuran

## NONPOINT
Person | Dataset | description | hierarchy | hierarchy rationale | QA | status
Roy | EPA PM Augmentation NP | fills in missing PM | 1
Roy | EPA Overwrite Nonpoint v1.5 | blocks some high values that came in from SLT | 2
Laurel | Rail_EPACorrections |  | 3
Roy | EPA Cr Split v2 | Correct Cr data from SLT and EPA datasets; newly developed by Roy for 2008v2 | 4
| Responsible Agency Data Set |  | 5
Laurel | EPA CMV |  | 6
Laurel | EPA Rail |  | 7
Roy | EIAG all in NP | these SCCs should have no point source component, hence the name, all in np. | 8
Tesh | 2008 EPA Ag Fires |  | 9
Roy | Misc NP Hg Cats | Add back Hg sources from older EI, like fluroescent light breakage | 10
Roy | EPA Possible Pt Source Contrib V1_5 | fills in missing indus and CI emissions | 11
Override Type | Override Value | description | hierarchy | rationale
SCC | 2810015000 |  | no datasets included | prescribed burning will be summarized outside of EIS along with other EVENTS
SCC | 2810020000 |  | no datasets included | prescribed burning will be summarized outside of EIS along with other EVENTS
Pollutant | 1746016 | 2,3,7,8-Tetrachlorodibenzo-p-Dioxin
Pollutant | 19408743 | 1,2,3,7,8,9-Hexachlorodibenzo-p-Dioxin
Pollutant | 3268879 | Octachlorodibenzo-p-Dioxin
Pollutant | 35822469 | 1,2,3,4,6,7,8-Heptachlorodibenzo-p-Dioxin
Pollutant | 39001020 | Octachlorodibenzofuran
Pollutant | 39227286 | 1,2,3,4,7,8-Hexachlorodibenzo-p-Dioxin
Pollutant | 40321764 | 1,2,3,7,8-Pentachlorodibenzo-p-Dioxin
Pollutant | 51207319 | 2,3,7,8-Tetrachlorodibenzofuran
Pollutant | 55673897 | 1,2,3,4,7,8,9-Heptachlorodibenzofuran
Pollutant | 57117314 | 2,3,4,7,8-Pentachlorodibenzofuran
Pollutant | 57117416 | 1,2,3,7,8-Pentachlorodibenzofuran
Pollutant | 57117449 | 1,2,3,6,7,8-Hexachlorodibenzofuran
Pollutant | 57653857 | 1,2,3,6,7,8-Hexachlorodibenzo-p-Dioxin
Pollutant | 600 | Dioxins/Furans as 2,3,7,8-TCDD TEQs - TEQ scheme unspecified
Pollutant | 60851345 | 2,3,4,6,7,8-Hexachlorodibenzofuran
Pollutant | 626 | Dioxins/Furans as 2,3,7,8-TCDD TEQs -I/89
Pollutant | 627 | Dioxins/Furans as 2,3,7,8-TCDD TEQs - WHO/98
Pollutant | 67562394 | 1,2,3,4,6,7,8-Heptachlorodibenzofuran
Pollutant | 70648269 | 1,2,3,4,7,8-Hexachlorodibenzofuran
Pollutant | 72918219 | 1,2,3,7,8,9-Hexachlorodibenzofuran

## NONROAD
Person | 2008v2 Sector or Dataset | Description | Default Hierarchy | QA | status
Laurel | EPA Correction Dataset - Nonroad | zero out emissions from pollutant/mode/process combinations that are not present in NMIM | not used
Laurel | Responsible Agency Data Set | SLT data, with PA corrected via script (EVP changed to EXH) | 1
Laurel | EPA Nonroad using NCD20101201 |  | 2
Laurel | EPA Nonroad using NCD20100602 |  | 3
Override Type | Override Value | Overwrite Hierarchy
State | California | 1, EPA Correction Dataset - Nonroad 2. Responsible Agency Data Set
Pollutant | 1746016 | 2,3,7,8-Tetrachlorodibenzo-p-Dioxin
Pollutant | 19408743 | 1,2,3,7,8,9-Hexachlorodibenzo-p-Dioxin
Pollutant | 3268879 | Octachlorodibenzo-p-Dioxin
Pollutant | 35822469 | 1,2,3,4,6,7,8-Heptachlorodibenzo-p-Dioxin
Pollutant | 39001020 | Octachlorodibenzofuran
Pollutant | 39227286 | 1,2,3,4,7,8-Hexachlorodibenzo-p-Dioxin
Pollutant | 40321764 | 1,2,3,7,8-Pentachlorodibenzo-p-Dioxin
Pollutant | 51207319 | 2,3,7,8-Tetrachlorodibenzofuran
Pollutant | 55673897 | 1,2,3,4,7,8,9-Heptachlorodibenzofuran
Pollutant | 57117314 | 2,3,4,7,8-Pentachlorodibenzofuran
Pollutant | 57117416 | 1,2,3,7,8-Pentachlorodibenzofuran
Pollutant | 57117449 | 1,2,3,6,7,8-Hexachlorodibenzofuran
Pollutant | 57653857 | 1,2,3,6,7,8-Hexachlorodibenzo-p-Dioxin
Pollutant | 600 | Dioxins/Furans as 2,3,7,8-TCDD TEQs - TEQ scheme unspecified
Pollutant | 60851345 | 2,3,4,6,7,8-Hexachlorodibenzofuran
Pollutant | 626 | Dioxins/Furans as 2,3,7,8-TCDD TEQs -I/89
Pollutant | 627 | Dioxins/Furans as 2,3,7,8-TCDD TEQs - WHO/98
Pollutant | 67562394 | 1,2,3,4,6,7,8-Heptachlorodibenzofuran
Pollutant | 70648269 | 1,2,3,4,7,8-Hexachlorodibenzofuran
Pollutant | 72918219 | 1,2,3,7,8,9-Hexachlorodibenzofuran

## FIRE
State | SCC | Data Source | Fire Type | Notes
Washington