Updated Team Members

- HEID – Beth Landis, Robin Langdon, Chris Davis, Carrie Wheeler, Sara Terry, Rob Pinder, Ben Gibson, *Amy Vasu (Air Toxics Strategy), Kimber Scavo, Darryl Weatherhead

- AQPD – Rich Damberg, *Monica Whalen (Advance Program Summer Intern)

- AQAD – Carey Jang, *Joe Mangino (Conceptual Model Detail in AQAG), Tyler Fox

- OID – *Amanda Kaufman (Environmental Justice)

*New Team Members – welcome!

Louisville Multi-Pollutant Project

Update

  - Spring 2020 - Louisville Metro Health Department provided higher spatial resolution data for BenMAP that has required a significant amount of QA

    - Data included zip codes outside of Jefferson county that needed to be excluded and some missing zip codes that were expected

    - Calculated incidence rates by zip code and age bin for all endpoints for 2017 & 2018

    - Comparison between LMHD and BenMAP data to ensure comparable – confirmed for mortality

    - Breaking the data down by zip code can result in choppy/missing data

Next Steps

  - July -

    - QA check of BenMAP vs. LMHD data for additional incidences, besides mortality, and call with LMAPCD and LMHD to determine best approach for aggregating data (e.g. neighborhoods, airsheds, E/W, etc.)

    - LMAPCD release final report & begin diving into recommendations

  - August –

    - Complete BenMAP analysis and discuss how to best communicate results

    - Call with LMAPCD regarding control strategies and AQMP

General Multi-Pollutant

Update

  - May 2020 – Participated in Advance Workgroup Call with EPA Regions to share MP concept and plans – R10 raised Portland as a potential partner worth exploring

  - June 2020 –

    - Followed-up with R4 regarding potential interest in MP partnership in FL and/or TN – awaiting response

    - Provided MP materials to Karl Pepple (R10) to share with Oregon and gauge interest

Next Steps

  - July 2020 – continue gauging interest in MP partnerships in FL, TN and/or OR

  - Summer/Fall 2020 – Develop regional packets using NEXUS Tool

NEXUS

Update

  - April/May 2020

    - Developed the NEXUS prototype (alpha version) to provide visualization and analysis functions of multi-pollutant air quality issues (PM2.5, O3 and air toxics) on a national level

    - Completed the new design of NEXUS tool's GUI, database and three key modules (Data Viewer, Data Query, and Data Input modules) and regional analysis (Phase 2) based on team’s feedback

  - June 2020 - Developed the NEXUS beta-version with new design of the three key modules and regional analysis

Next Steps

  - July/August 2020

    - Start testing, debugging and improving the NEXUS Tool; giving demo when ready

    - Develop on-line User’s Manual

Potential Detroit Multi-Pollutant Project

Update

  - April 13, 2020 – call with Region 5 and MI EGLE to discuss their interest in a MP risk-based analysis in Detroit

    - Michigan Ontario Ozone Source Experiment (MOOSE) study likely being pushed back due from Summer 2020 to Summer 2021 - $$ was swept for COVID-19

    - EGLE sees benefits of MP approach but has concerns about actually implementing the control strategies that are chosen

    - Timeframe for SIP development and submittal would make it difficult to fit in this type of work and still meet the CAA requirements

Next Steps

- EGLE & R5 having internal discussions about potential MP work

- July 2020 – follow-up with MI and R5 regarding outcome of discussions

US/Mexico Border Multi-Pollutant Project

Update

  - Continued engagement in El Paso/Juarez, Imperial County/Mexicali & San Diego/Tijuana to identify opportunities for OAQPS collaboration, including:

    - Emissions inventory development

    - Improved monitoring (including sensors)

    - Trainings (e.g. BenMAP, sensors, etc.)

    - Sustainable funding mechanisms

  - Cross-border multi-pollutant pilot program still possible after success with smaller projects

  - April 14, 2020 – Peter Briefing on US-Mexico Border Strategy Update

  - Spring 2020 – drafted strategic goals document for Peter

Next Steps

- Summer 2020 – Peter briefing to share draft strategic goals

Mobile Control Measures Project

Update

  - March/April 2020 - Requested courtesy review of results by OTAQ

  - May 7, 2020 – call with OTAQ to provide background on the purpose of the project, what it is intended to be used for, who the audience would be, etc.

  - June 2020 – OTAQ provided feedback

Next Steps

  - July 2020 – review comments from OTAQ and determine best way to incorporate

  - Summer 2020 - more broadly share workbook

Next Team Meeting Scheduled for Tuesday, July 28th at 11am