Team Members

- HEID – Beth Landis, Robin Langdon, Chris Davis, Carrie Wheeler, Sara Terry, Rob Pinder, Ben Gibson, Scott Voorhees, Amy Vasu, Matt Woody, Kimber Scavo, Darryl Weatherhead, Kelly Rimer

- AQPD – Rich Damberg

- AQAD – Carey Jang, Joe Mangino, Jeanette Reyes, Tyler Fox

- OID – Amanda Kaufman

- SPPD – Lisa Conner – WELCOME!

NEXUS

Update

·       Developed a fully working NEXUS tool, a draft online User's Manual, and made improvements based on team’s feedback (Dec. 2020)

  - Winter 2020/2021 briefings/demos for all divisions and Peter/SMT

  - HEID/AQAD briefing (4/12/2021)

  - Development team creating beta version

  - Revising national air toxic metrics

  - Incorporated EJ/demographic index from EJSCREEN and Tribal areas

  - Updating to 2017 emissions (including GHG & Sector mapping) and air quality data

- Updating O3 and PM2.5 risk data (BenMAP)

  - Working to demonstrate potential of sector prioritization in NEXUS

Next Steps

  - Spring 2021 –

    - Demo NEXUS 1.7 for MP Team (Beth will schedule)

    - MP Team Members

        - Download NEXUS 1.5 or 1.7 via EISD and provide feedback

    - Briefings/demos for:

        - Peter (scheduled for 5/10/2021 at 2pm)

        - Region 4/Louisville

        - APMs

        - MJOs

    - Incorporate feedback received from briefings/demos

  - Summer/Fall 2021 –

    - Develop a beta NEXUS version for testing (and prepare for public release?)

    - Finalize online User’s Manual

    - Develop packets for regions

  - Consider incorporating Mexico (border) information into NEXUS

  - Issue - Funding support & contract vehicle

Louisville Multi-Pollutant Project

Update

  - January Meeting with LMAPCD

    - Discussed major NOx point sources in Jefferson Co, NAA, KY, IN & OH

    - Upcoming transport conversations – how LMAPCD can engage w/ Regions

  - March Meeting with LMAPCD

    - Ali discussed BenMAP results

Next Steps

  - Small strategizing meeting with LMAPCD tomorrow (5/5/2021) to discuss next steps

General Multi-Pollutant

Update

  - Possible Future MP Work:

    - FL and/or TN – raised by R4 as possibilities – R4 currently exploring interest

    - Detroit, MI – raised by R5/MEGLE as possibly interested in MP work in conjunction with Michigan-Ontario Ozone Source Experiment (MOOSE) – trying to reschedule to summer 2021 due to Covid-19

    - Portland, OR – raised by R10 as potential partner worth exploring during Advance Workgroup Call – sent materials to Karl Pepple to determine interest

    - US/Mexico Border - cross-border MP pilot program possible after success is demonstrated with smaller projects (EI development, improved monitoring, trainings) – interest from Guy Donaldson (El Paso) & Idalia Perez (Imperial & San Diego)

  - February – Kimber spoke on call with APMs about collective efforts in the MP and Advance programs that will be coming

Next Steps

  - Spring/Summer 2021 -

    - Continue gauging interest in MP partnerships in FL, TN, Detroit, Portland and/or US/Mexico Border

    - Explore El Paso, Imperial & San Diego in NEXUS

    - Once latest NEXUS updates completed, create regional packets

Mobile Control Measures Project

Update

  - Spring 2020 - Requested courtesy review of results by OTAQ

  - Summer 2020 –

    - Call with OTAQ to provide background on the purpose of the project, what it is intended to be used for, who the audience would be, etc.

    - OTAQ provided feedback

    - Began reviewing comments from OTAQ to determine best way to incorporate

Next Steps

  - Spring 2021 -

    - Finish incorporating comments from OTAQ

    - More broadly share workbook

Next Team Meeting Scheduled for Tuesday, June 1st at 11am