Team Members

- HEID – Beth Landis, Robin Langdon, Chris Davis, Carrie Wheeler, Sara Terry, Rob Pinder, Ben Gibson, Amy Vasu, Kimber Scavo, Darryl Weatherhead

- AQPD – Rich Damberg

- AQAD – Carey Jang, Joe Mangino, Tyler Fox

- OID – Amanda Kaufman

Louisville Multi-Pollutant Project

Update

  - November Meeting with LMAPC

    - Shared initial BenMAP run results using county level health data

    - Discussed different ways to pool the data – East/West, percent minority, urban/suburban, etc.

Next Steps

  - BenMAP

    - Explore best ways to pool data, schedule follow-up meeting if necessary

  - December call with LMAPCD

    - Discuss next steps with LMAPCD’s regulated sources and regulatory partners at KYDAQ and IDEM

NEXUS

Update

  - Developed the NEXUS prototype (alpha version) to provide visualization and analysis functions of multi-pollutant air quality issues (PM2.5, O3 and air toxics) on a national level

  - Developed the NEXUS beta-version with new design of the three key modules (Data Viewer, Data Query, and Data Input) and regional analysis (Phase 2), based on team’s feedback

  - Demoed NEXUS at the July MP Team Meeting & again in November

  - Continued testing, debugging and improving NEXUS Tool based on feedback received

  - Drafted online User’s Manual

  - Briefed Chet & Erika in September AQAD Technical Meeting

  - Success downloading NEXUS 1.5 through request to EISD

  - NEXUS demo/meeting with air toxics group in November

Next Steps

  - Fall/Winter 2020 –

    - MP Team Members - download NEXUS 1.5 via EISD and provide feedback

    - Incorporate feedback from air toxics group

    - Begin briefings/demos for:

        - Peter

        - Region 4/Louisville

        - APMs

        - MJOs

    - Finalize online User’s Manual

No Major Changes Since October Meeting….

General Multi-Pollutant

Update

  - Possible Future MP Work:

    - FL and/or TN – raised by R4 as possibilities – R4 currently exploring interest

    - Detroit, MI – raised by R5/MEGLE as possibly interested in MP work in conjunction with Michigan-Ontario Ozone Source Experiment (MOOSE) – trying to reschedule to summer 2021 due to Covid-19

    - Portland, OR – raised by R10 as potential partner worth exploring during Advance Workgroup Call – sent materials to Karl Pepple to determine interest

    - US/Mexico Border - cross-border multi-pollutant pilot program possible after success is demonstrated with smaller projects (e.g. EI development, improved monitoring, trainings)

  - August 2020 - Drafted email that gives Regional contacts a heads up about collective efforts in the MP and Advance programs that will be coming this fall

Next Steps

  - Fall/Winter 2020

    - Continue gauging interest in MP partnerships in FL, TN, Detroit, Portland and/or US/Mexico Border

    - Send MP/Advance email to regions so they are aware of next steps and can prepare to engage

    - Develop regional packets using NEXUS Tool

Mobile Control Measures Project

Update

  - Spring 2020 - Requested courtesy review of results by OTAQ

  - Summer 2020 –

    - Call with OTAQ to provide background on the purpose of the project, what it is intended to be used for, who the audience would be, etc.

    - OTAQ provided feedback

    - Began reviewing comments from OTAQ to determine best way to incorporate

Next Steps

  - Fall 2020 –

    - Finish incorporating comments from OTAQ

    - More broadly share workbook

Next Team Meeting Scheduled for Tuesday, December 15th at 11am